## README
FCC-Style Resource Planning & Tracking Model
Self-initiated Excel exercise by Priscilla Judi, 2026. ALL DATA IS FICTIONAL.
Work packages are loosely themed on the public Future Circular Collider feasibility study areas; teams, effort and dates are invented for illustration. Not CERN data and not affiliated with CERN.
How it works
1. Capacity: teams and monthly capacity in person-months (blue = editable input).
2. Tasks: work packages with owner team, start/end month (1-12) and total effort. Monthly load is calculated.
3. Allocation: SUMIFS spreads each task's load across its months by team; utilisation = load / capacity.
Red > 100% (over-allocated), amber 85-100% (near limit), green < 85%.
4. Checks: data-quality tests (missing owner, End before Start, duplicate IDs, months out of range, unknown team).
5. Summary: headline metrics and peak utilisation chart by team.
Tools: Excel / Google Sheets - SUMIFS, COUNTIFS, SUMPRODUCT, INDEX/MATCH, conditional formatting, data validation, charts.

## Summary
Summary - Resource Utilisation
Work packages | 17
Total planned effort (person-months) | 340
Team-months over 100% capacity | 16
Team-months at 85-100% capacity | 10
Team with highest peak utilisation | Detectors & Experiments
Highest peak utilisation | 133.3%
Data-quality checks passed | 6 of 6
Team | Peak utilisation
Civil Engineering & Siting | 110%
Accelerator Physics | 112.5%
Magnets & Cryogenics | 128.6%
Detectors & Experiments | 133.3%
Planning & Resources Office | 120%

## Capacity
Team | Headcount | Capacity (person-months / month)
Civil Engineering & Siting | 10 | 10
Accelerator Physics | 8 | 8
Magnets & Cryogenics | 7 | 7
Detectors & Experiments | 6 | 6
Planning & Resources Office | 5 | 5
Capacity assumes 1.0 person-month per head per month (no leave/overhead). Edit headcount in blue.

## Tasks
Task ID | Work package | Team | Start month | End month | Total effort (person-months) | Monthly load | Status
WP-01 | Geology & tunnel siting review | Civil Engineering & Siting | 1 | 4 | 20 | 5 | Complete
WP-02 | Environmental baseline study | Civil Engineering & Siting | 3 | 8 | 24 | 4 | In progress
WP-03 | Surface sites & access shaft layout | Civil Engineering & Siting | 5 | 10 | 30 | 5 | In progress
WP-04 | Civil cost estimate inputs | Civil Engineering & Siting | 7 | 9 | 6 | 2 | Not started
WP-05 | Collider lattice & optics design | Accelerator Physics | 1 | 6 | 30 | 5 | In progress
WP-06 | Beam dynamics & collimation studies | Accelerator Physics | 4 | 9 | 24 | 4 | In progress
WP-07 | Injector chain requirements | Accelerator Physics | 7 | 12 | 18 | 3 | Not started
WP-08 | Superconducting magnet R&D review | Magnets & Cryogenics | 1 | 8 | 40 | 5 | In progress
WP-09 | Cryogenic system layout | Magnets & Cryogenics | 5 | 11 | 28 | 4 | Not started
WP-10 | Vacuum system specification | Magnets & Cryogenics | 9 | 12 | 16 | 4 | Not started
WP-11 | Detector concept requirements | Detectors & Experiments | 2 | 7 | 24 | 4 | In progress
WP-12 | Physics case & performance studies | Detectors & Experiments | 6 | 12 | 28 | 4 | Not started
WP-13 | Stakeholder requirements gathering | Planning & Resources Office | 1 | 3 | 9 | 3 | Complete
WP-14 | Master schedule baseline & milestones | Planning & Resources Office | 2 | 6 | 15 | 3 | In progress
WP-15 | Resource-loaded plan & tracking tool | Planning & Resources Office | 4 | 9 | 12 | 2 | In progress
WP-16 | Data quality & plan-update process | Planning & Resources Office | 8 | 12 | 10 | 2 | Not started
WP-17 | Risk register & contingency review | Planning & Resources Office | 10 | 12 | 6 | 2 | Not started

## Allocation
Monthly load by team (person-months)
Team | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
(month number) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Civil Engineering & Siting | 5 | 5 | 9 | 9 | 9 | 9 | 11 | 11 | 7 | 5 | 0 | 0
Accelerator Physics | 5 | 5 | 5 | 9 | 9 | 9 | 7 | 7 | 7 | 3 | 3 | 3
Magnets & Cryogenics | 5 | 5 | 5 | 5 | 9 | 9 | 9 | 9 | 8 | 8 | 8 | 4
Detectors & Experiments | 0 | 4 | 4 | 4 | 4 | 8 | 8 | 4 | 4 | 4 | 4 | 4
Planning & Resources Office | 3 | 6 | 6 | 5 | 5 | 5 | 2 | 4 | 4 | 4 | 4 | 4
Utilisation (load / capacity)
Team | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | Peak | Months >100% | Months 85-100%
Civil Engineering & Siting | 50% | 50% | 90% | 90% | 90% | 90% | 110% | 110% | 70% | 50% | 0% | 0% | 110% | 2 | 4
Accelerator Physics | 62.5% | 62.5% | 62.5% | 112.5% | 112.5% | 112.5% | 87.5% | 87.5% | 87.5% | 37.5% | 37.5% | 37.5% | 112.5% | 3 | 3
Magnets & Cryogenics | 71.43% | 71.43% | 71.43% | 71.43% | 128.6% | 128.6% | 128.6% | 128.6% | 114.3% | 114.3% | 114.3% | 57.14% | 128.6% | 7 | 0
Detectors & Experiments | 0% | 66.67% | 66.67% | 66.67% | 66.67% | 133.3% | 133.3% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 133.3% | 2 | 0
Planning & Resources Office | 60% | 120% | 120% | 100% | 100% | 100% | 40% | 80% | 80% | 80% | 80% | 80% | 120% | 2 | 3

## Checks
Data-quality check | Issues found | Result
Tasks with missing team | 0 | OK
Tasks with End before Start | 0 | OK
Duplicate Task IDs | 0 | OK
Months outside 1-12 | 0 | OK
Team not in Capacity list | 0 | OK
Tasks with missing effort | 0 | OK